## Sheet1
Week Periode | 01/07/2024 - 01/07/2024
Department: | Information Technology
Key Highlights | - Sobot changes for meet the CS needs.
- IoS launching preparation
- Remove old server in Alicloud
- New website
- Competitor Research
- Aurora dashboaord Apollo report
| Name | Description | Status | Task / Issue | Details
Products | Website Samir | Monitoring & Maintaining our Website | development | - Changing website from alicloud to whuawei (DONE) | - New website samir already moving to the huawei cloud.
| Sobot | Monitoring and supporting our CRM platform | Stable / Progress | - Setup outbound call using premium number (DONE) - Sobot CSAT review on facebook can't appear on the messanger and application. | - Sobot CRM can make a outbound call using our premium number - Facebook have a prohibition related to their CSAT feature. We still coolaboration with sobot to figure it out how to solving this problem
| Recurent | Monitoring and supporting Our QA platform | Stable / Progress | - No Issue this week | Reccurent data is so little from Friday 15 data and Saturday only 7 data
| Android App | Learning, Monitoring & Supporting | Stable | - Automatic phone number select on login page (DONE) - Google play console review sometimes can't appear on android device (DONE) | - We want to put automatic selection phone number to select their phone number inside the android phone. - Google android review popup to enforce our user to give a review on our google play console
| Dashboard | Learning, Monitoring & Supporting | Stable | - There is a strange error on telemarketing issue (DONE) - | - Some telemarketing agent can't insert the content and record disappear in their data
| iOS App | Developing & Preparation for OJK Submition | Progress | - While waiting for the iOS submission to OJK, we are trying to add features like on Android, such as Live Chat. | - While waiting for the iOS submission to OJK, we are trying to add features like on Android, such as Live Chat.
| Ai Ruder | Our collection team already used the AI Ruder for the collection to do automatic call and predictive call | Stable | - IT Support team monitor AI Ruder | the daily activity for calling and and productive call data uploaded by excel into ai ruder dashboard
| Research | We conduct product research with existing competitors and vendors. | On Progress | - Registration some of vendor or competitor | There is no error found in AI ruder
Projects | Research Employee Behavior Monitoring Tools for monitoring and security. | We have initiatives to use tools that can monitor activity, behavior and security on company devices used by employees. | Blocked | Pricing negotiation with SearchInform (BD Side) | - The price already given waiting to decision. (DONE) - Testing the server once again to know the working process in server side.(DONE) - Waiting the decision
| Research risk vendors | We plan to enhance our risk engine capability with using or research another risk vendors | Blocked | - Back testing data TSI | - We are waiting back testing data from SH team.
| Pusdafil 2.0 Report | We must using version 2.0 for pusdafil reporting | Progress | We already report pusdafil 2.0 and having some error | - Pusdafil 2.0 report already released, we are still monitoring and fixing
| BSS Channeling | We will doing the channeling cooperation with bank sampoerna or BSS | Progress | - Waiting business process '- UAT simulation with dummy data - Waiting commercial things in business side for API bank transfer | - Discussion related to business and technical with BSS still working.
| New Project Code Collecttion | The new project given to me to makesure the code can be run | Progress | - runing 2 projects into our local server | - The project already in our local server, still configuration in domain to make a server can be accessed from the outside.
IT Operations | Office network | Monitoring & Maintaining our network | Stable | - Office network is stable on Kemang & Mayapada office, now we want to create an access for the guest. | - Guest access is
| IT Asset | Monitoring & Maintaining our IT Asset | Done | - Overall the the assets is working well - Fixing unrecord asstes who belongs to jayindo (Checking The Asset is work or not) | - Overall the the assets is working well - We have unrecord assets because its belong to Jayindo - Since we already migrating the website all system to huawei server then we will remove old server from the alicloud.
| Support | Supporting the operations | Stable | - our network and operational support are stable and have no major incidents | - our network and operational support are stable and have no major incidents
| iOS submission | - Preparing all regulation need for iOS submission to OJK | Progress | - Preparing all regulation need for iOS submission to OJK | - We are focusing in risk tracing
Security & Compliance | SOP | Monitoring the SOP | Stable / Progress | - Fixing the SOP to inline with current condition. | - We will makesure all sop is fit with the current condition.
| Recurent | Reccurent is our QA Tools to monitoring and analyzing our QA based on AI | Initiative | - No Issue | - No Issue
| Regulation Reporting | Provide the reporting silaras for OJK | DONE | - No Issue | - No Issue
| Data Processing | ID Local team must be able to provide the data for all department | Initiative | - Finance Data (Finish / Need to reconsile and monitoring) - Silaras Report (Finish/Need to testing and compare) - APUPPT Report - Collection Daily Report. - OJK Self Assesment data | -Having problem with the repayment data for income sharing still not clear in reporting data. This is we still back to back communication between shanghai team data & finance with local team data and finance
| Prepare the self assesment checklist and data from OJK | Preparing self assesnt checkist | Progress | - Done | - Form self assesment data asking by OJK we make a summarize of results in here: https://docs.google.com/spreadsheets/d/1U6nlPhiCORvkt4L8W330HwX7KYLqwn7K/edit?usp=sharing&ouid=115832971917175031706&rtpof=true&sd=true
Resource Allocation and Planning | Resources | Resources allocation monitoring in IT department | Stable | QA Team | Making the QA Assessment test for the candidate
| Training | Training to increase the skill and knowledge | Progress | - Risk Training With the Risk team | - we already have a training with shanghai risk team and still waiting to sync with the IT System
| 1 on 1 meeting | We are doing the monthly 1 on 1 meeting with the team | Stable | - 1 on 1 meeting with android developer | - Having a meeting with android developer, the process is satified and the input from him. Need more task for android.
Social media | Social Media monitor | Our social media should be monitored so that we can increase awareness of our customers or potential new customers. | Preparation | - All the social media report related to social media movement and comment can be read in our google sheet on the google drive | - We have a problem with instagram verification because instagram rejected our verification request again.
| Strategies | Marketing plan must be inline with the social media plan | Preparation | Discussion for mascot
| Problems | Bluetick in meta platform such as Instagram & Facebook | Preparation | - Bluetick(Verification in Meta Platform) - Testing to submit again but failed
Upcoming Initiatives
Collection Apps | - Project already can be run in our local server in kemang office, right know we are trying to configure the server can be access from the outside.
Comparation between dashboard production and development | Done
iOS Preparation | - We are doing the new and reloan testing in production environment using the iOS. The problems still checking some words and flow makesure again. - Back to back with Risk Manager to know and understand more deeply in Risk Process for iOS. - Need to doing the live demo colaboration with risk
Data | - Silaras Dashboard in Our Bigdata Dashboard(Aurora), his dashboard can be used for compliance & operation team to make a silaras report. - Our database team already can send the daily report for collection team and finances for monthly and weekly - New report from apolo already in Aurora Dashboard. - Finance dashboaard from databases in AURORA (Still makesure the data with binbin and michael) - Operational dashboard from databases in AURORA Dashboard (On Process) - Need to prepare the query for all of OJK question during the audit
Social Media | - Need to monitor the ads also, because we have an expense in advertising so i think our social media(Manesha) Should know the ads processing because need to makesure this flow and process inline with the SOP
Office Network | - Device monitoring who connect to our network
Risk Machine | Cooporation with risk manager to know the flow in logict and system (Still waiting Risk Manager to learn the risk flow first)
Samir Playbook | - I think this times samir must have a Playbook / User guidance for all employee to know how to process the system. This guidance will given to Trainer so trainer can manage the content for onboarding in each departments need
Problems, Challenges and Risks
OJK Audit Preparation | - Need to migrate all the server to huawei because huawei have a complied archithecture. - Checking SOP and all process need to do before audit time come |  |  |  | Done
Database's Access | After migration to huawei we still waiting the access to databases |  |  |  | Done
Machine Access | After migration to huawei we still waiting the access to all of our machine server |  |  |  | Done
Data Flow | Currently we found Aurora and Bigdata using airflow to sending the data from databases to our data lake and consume in bigdata and aurora for display, we must to think to how we will explain it to the OJK, I have a suggestion to make a duplicate data flow and activate it when the ojk come |  |  |  | Done
Provide data to all department | - Trying to provide iInsentive data for Collection, CS, Tele departments |  |  |  | Done
Samir Brand Identity | Samir must have a brand identity so that every post on social media or online media has a clear identity about Samir. |  |  |  | Done
Design flow process for Social media & Design team | The design team should have a process that flows to other departments that require publication on all social media or if they require material design. |  |  |  | Done
Money Flow | We need to know end to end money flow from the system |  |  |  | Challenges
Risk Machine | We need to know end to end the risk logict and risk machine running in our system |  |  |  | Challenges